## Summary
River DMS - E2E Automation Test Cases
Enquiry List, GSTR and MIS test cases executed on 25-Sep-2026; PDI Vehicle Details and ENQ-16/17 on 28-Sep-2026; PDI master, tracking and email cases (PDI-25 to PDI-32) on 01-Oct-2026 — all against the live DMS (Microsoft Edge and Google Chrome). PDI-29 / PDI-30 are pending the report owner's review of the email. Stage DMS flow (STG-01 to STG-05) on 06-Oct-2026 against the stage DMS (Google Chrome).
Sheet | Script | Total | Positive | Negative | Edge | Passed | How to run
Enquiry List | tests/enquiryListReport.spec.ts | 16 | 14 | 1 | 1 | 16 | npx playwright test tests/enquiryListReport.spec.ts
GSTR Report | tests/GSTR Report.spec.ts | 20 | 10 | 5 | 5 | 20 | npx playwright test "tests/GSTR Report.spec.ts"
MIS Report Check | run_mis_check.js | 23 | 12 | 7 | 4 | 23 | npm start (on a server: CI=1 BROWSER_CHANNEL=chromium node run_mis_check.js)
PDI Vehicle Details | tests/PDI.spec.ts (+ tests/PDIDailyReport.spec.ts) | 33 | 19 | 9 | 5 | 30 | npm run test:pdi (dry run: npm run test:pdi:dry; daily report: npm run report:pdi-daily)
Stage DMS Flow | tests/Automation for Testing.spec.ts | 5 | 5 | 0 | 0 | 5 | npx playwright test "tests/Automation for Testing.spec.ts"
Total |  | 97 | 60 | 22 | 15 | 94

## Enquiry List
Enquiry List - tests/enquiryListReport.spec.ts
Dealer login, Enquiry List report, Product-wise Sales Details (Invoice + Booking date types) and a combined Enquiry / Invoice / Booking summary by date and dealer.
Run: npx playwright test tests/enquiryListReport.spec.ts
TC ID | Feature | Test Scenario | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Status | Remarks
ENQ-01 | Login | Dealer logs in with valid credentials | Positive | High | dealervalidUser in credentials.json | 1. Open DMS login page 2. Enter Dealer Code, Tab (branch loads) 3. Enter User Name, Password 4. Click Sign In | dealervalidUser | Dashboard caption and Sales/Service Dashboard link are visible | Pass (25-Sep-2026) | Run on Edge (BROWSER_CHANNEL=msedge). Google Chrome is now installed, so the default channel works too.
ENQ-02 | Navigation | Open Enquiry List report | Positive | High | Logged in | MIS > MFR Vehicles Reports > Pre-sales > Enquiry List |  | Enquiry List filter screen is shown | Pass (25-Sep-2026)
ENQ-03 | Filters | Set date range through the calendar | Positive | High | Enquiry List open | 1. From Date calendar: step back to September 2026, pick 7 2. To Date: pick today | From 07-09-2026, To today | Both date boxes show the chosen dates | Pass (25-Sep-2026) | From date is hard-coded to 7 Sep 2026 in the spec. To date now defaults to yesterday (changed 01-Oct-2026; not re-run since).
ENQ-04 | Report viewer | View Report opens the viewer in a new tab | Positive | High | Dates set | 1. Click View Report 2. Wait for new tab 3. Open "Select the columns" panel |  | Report viewer tab opens with the grid and column selector | Pass (25-Sep-2026)
ENQ-05 | Data check | Enquiry record count is greater than 0 | Positive | High | Viewer open | 1. Count grid rows (excluding header) 2. Show count in a browser alert |  | Count > 0; alert "Enquiry List record count: N" | Pass (25-Sep-2026) | 20,113 enquiries
ENQ-07 | Large report | More than 1000 enquiries (over the viewer display limit) | Edge | High | Range with >1000 rows | 1. View Report 2. Viewer shows display-limit banner and downloads Excel 3. Rows read from the Excel file |  | All rows read from the download (header row found by Dealer Code); counts match the file | Pass (25-Sep-2026) | All three reports were over the limit: Enquiry 20,113, Invoice 3,171, Booking 4,709 rows - all read from the Excel download
ENQ-08 | Data check | Dealer codes extracted | Positive | Medium | Rows read | Read Dealer Code column by header name |  | Dealer code list and distinct dealer count logged | Pass (25-Sep-2026) | 87 distinct dealers (Enquiry), 84 (Booking)
ENQ-09 | Summary | Enquiries grouped by Date / Dealer Code / Dealer Name | Positive | Medium | Rows read | Group rows; print table with Total row |  | Table printed; Total = record count | Pass (25-Sep-2026) | Total row = 20,113
ENQ-11 | Product-wise Sales | Invoice date type report in the same session | Positive | High | Enquiry viewer closed | 1. MIS > MFR Vehicles Reports > Sales > Product-wise sales details 2. Same dates 3. View Report | Date type: Invoice (default) | Invoice rows read; counted by distinct Booking No | Pass (25-Sep-2026) | 3,171 invoice rows
ENQ-11a | Product-wise Sales | Invoice dealer codes counted | Positive | Low | Invoice rows read | Read Dealer Code column of the Invoice rows |  | Log "Dealer codes: N rows, M distinct dealers" (like Enquiry and Booking) | Pass (25-Sep-2026) | Google Chrome run: "Dealer codes: 3239 rows, 83 distinct dealers" for Invoice
ENQ-12 | Product-wise Sales | Booking date type report | Positive | High | Invoice viewer closed | 1. Go home via header logo 2. Re-open Product-wise sales details 3. Set Date Type = Booking 4. View Report | Date type: B | Booking count > 0; alert with count | Pass (25-Sep-2026) | 4,709 booking rows
ENQ-13 | Summary | Combined Enquiry / Invoice / Booking summary | Positive | High | All three row sets read | Merge by Date + Dealer; add Total row |  | Combined table printed; combined-summary.csv attached to the test result | Pass (25-Sep-2026) | Totals 20,113 / 3,171 / 4,709; combined-summary.csv attached
ENQ-14 | Reporting | Combined summary emailed | Positive | Medium | GMAIL_* set in .env | Test run ends |  | Gmail reporter emails the CSV as an HTML table | Pass (25-Sep-2026) | Emailed to sunita@rideriver.com with 1 report pasted in the body
ENQ-15 | Setup | Credentials from another file (CI secret) | Positive | Medium | CREDENTIALS_FILE points to a valid credentials.json | CREDENTIALS_FILE=<path> npx playwright test tests/enquiryListReport.spec.ts |  | Test logs in with the users from that file | Pass (25-Sep-2026) | CREDENTIALS_FILE pointed to a copy of credentials.json; logged in and passed in 55s
ENQ-16 | Setup | Report dates from settings | Positive | Medium | ENQ_FROM / ENQ_TO set | ENQ_FROM=20-09-2026 ENQ_TO=27-09-2026 npx playwright test tests/enquiryListReport.spec.ts | ENQ_FROM=20-09-2026, ENQ_TO=27-09-2026 | All three reports use that range | Pass (28-Sep-2026) | Passed in 46 s: 10,596 enquiries / 1,361 invoices / 1,815 bookings
ENQ-17 | Setup | Date setting in the wrong format | Negative | Low | ENQ_FROM=2026/09/01 | Run the test |  | Stops at once: "ENQ_FROM must be dd-mm-yyyy" | Pass (28-Sep-2026) | Exact message seen

## GSTR Report
GSTR Report - tests/GSTR Report.spec.ts
For every dealer in credentials.json: ProductWise Sales Details (GSTR Reports) for 01-09-2026 to 24-09-2026, Post GST Discount read from each Product Sale invoice PDF, one Excel per dealer plus a MasterData file.
Run: npx playwright test "tests/GSTR Report.spec.ts"
TC ID | Feature | Test Scenario | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Status | Remarks
GSTR-01 | Setup | credentials.json has no dealers / missing fields | Negative | High | Empty dealerUsers, or a dealer without username/password | Start the test |  | Fails at once with a message naming the incomplete dealer(s); nothing is run | Pass (25-Sep-2026) | Empty dealerUsers -> "has no dealerUsers"; dealer without password -> "missing for 291001"; both stopped at once
GSTR-02 | Login | Each dealer logs in with valid credentials | Positive | High | 7 dealers in dealerUsers | Dealer Code + Tab, User Name, Password, Sign In | dealerUsers | Dashboard shown for each dealer | Pass (25-Sep-2026) | 7/7 dealers
GSTR-03 | Login | Wrong password for one dealer | Negative | High | One dealer with a bad password | Run the test |  | "Login failed: still on the login page" logged; screenshot attached; dealer retried once at the end; other dealers complete; MasterData saved; test marked failed listing that dealer | Pass (25-Sep-2026) | Test copy of 331001 with a wrong password: "Login failed: still on the login page"; screenshot attached; retried once; 291001 completed
GSTR-04 | Navigation | Open ProductWise Sales Details | Positive | High | Logged in | MIS > Accounts Reports > GSTR Reports > ProductWise Sales Details |  | Report filter screen shown | Pass (25-Sep-2026)
GSTR-05 | Filters | Date range set and verified | Positive | High | Report open | 1. Pick 1 Sep 2026 and 24 Sep 2026 in the calendars 2. Read both boxes back | 01/09/2026 - 24/09/2026 | Log "Report dates: 01/09/2026 to 24/09/2026" | Pass (25-Sep-2026)
GSTR-06 | Filters | Calendar click lands on the wrong box (headed window) | Edge | Medium | From calendar popup overlaps To box | Set dates |  | [WARN] logged and the correct date typed in; run continues; fails the dealer only if dates still wrong | Pass (25-Sep-2026) | Calendar could not reach Jan 2020 / To box covered by the popup -> dates typed in (01/01/2020 - 02/01/2020)
GSTR-07 | Report data | Report up to 1000 rows read from the grid | Positive | High | Dealer with <=1000 rows | View Report; read grid | e.g. 271001 (158), D71001 (846) | All grid rows read; count logged | Pass (25-Sep-2026)
GSTR-08 | Report data | Report over 1000 rows read from the Excel download | Edge | High | Dealer with >1000 rows | 1. Viewer shows display-limit banner 2. Excel downloads (or "click here") 3. Rows read from the file | 321001 (1096 rows) | All 1096 rows read; header row found without a Dealer Code column | Pass (25-Sep-2026) | Failed on 25-Sep before the fix ("Dealer Code header row not found").
GSTR-09 | Report data | Dealer with no records for the range | Edge | Medium | Dealer with 0 rows | Run the dealer |  | Warning annotation; empty file saved; run continues | Pass (25-Sep-2026) | 01-01-2020 to 02-01-2020: 0 rows, warning logged, empty file saved, test passed
GSTR-10 | Discount lookup | Post GST Discount read from the invoice PDF | Positive | High | Product Sale row with an invoice | 1. Product Sale Work Sheet: search Reference No 2. Wait for the search to finish 3. Print Invoice 4. Download PDF, read "Post GST Discount" | e.g. 291002/26/IND/6 | DiscountAmount set from the PDF (e.g. 0) | Pass (25-Sep-2026) | 367 Product Sale rows across 7 dealers
GSTR-11 | Discount lookup | Booking not invoiced yet | Edge | Medium | Reference with no Print Invoice option | Search the booking | e.g. 00184074 | Logged "not invoiced"; DiscountAmount left as in the report | Pass (25-Sep-2026) | ~60 such bookings on 25-Sep
GSTR-15 | Output | Per-dealer Excel saved | Positive | High | Dealer finished | Save rows |  | Output/<dealer>_SalesGSTNReport_01-09-2026_24-09-2026.xlsx with No. 1..N first, 45 columns, DiscountAmount normalised | Pass (25-Sep-2026) | 7 files verified
GSTR-16 | Output | MasterData combines all dealers | Positive | High | All dealers done | Save MasterData |  | Rows = sum of dealer files; No. 1..N across all dealers; credentials order | Pass (25-Sep-2026) | 4137 rows = 158+399+846+1096+910+727+1
GSTR-17 | Resume | Rerun after an interrupted run | Edge | High | Some dealer files already in Output | Run the test again |  | Finished dealers reused (logged "already saved"); only missing dealers run; GSTR_RERUN_ALL=1 forces all | Pass (25-Sep-2026) | Used 3 times on 25-Sep
GSTR-18 | Output | Output file open in Excel | Negative | Medium | MasterData open in Excel | Run the test |  | [WARN] and file saved as <name>_<timestamp>.xlsx; run not lost | Pass (25-Sep-2026) | MasterData locked (as by Excel): EBUSY -> saved as MasterData_..._<timestamp>.xlsx
GSTR-19 | Session | Clean session between dealers | Positive | Medium | Dealer finished or failed | Next dealer starts |  | Extra tabs closed; logout (or cookies cleared if logout link missing); next login starts clean | Pass (25-Sep-2026)
GSTR-20 | Recovery | Dealer still fails after its retry | Negative | High | Persistent failure for one dealer | Run the test |  | MasterData saved with the other dealers; test fails (red in CI) naming the dealer; rerun fills it in | Pass (25-Sep-2026) | MasterData saved with 1/2 dealers; test failed naming 331001
GSTR-21 | CI / server | Headless run with CI=1 | Positive | High | No visible window | CI=1 BROWSER_CHANNEL=msedge npx playwright test "tests/GSTR Report.spec.ts" |  | Window maximize skipped quietly; test passes | Pass (25-Sep-2026) | Passed in 15s (6 dealers reused, 291001 re-run); MasterData identical
GSTR-22 | Setup | Credentials, output folder and dates from settings | Positive | Medium | CREDENTIALS_FILE, GSTR_OUTPUT_DIR, GSTR_FROM / GSTR_TO set | Run the test with the settings | GSTR_FROM=01-01-2020, GSTR_TO=02-01-2020 | Uses that file, writes to that folder, reports those dates | Pass (25-Sep-2026) | Used for every negative test on 25-Sep
GSTR-23 | Setup | Date setting in the wrong format | Negative | Low | GSTR_FROM=2026/09/01 | Run the test |  | Stops at once: "GSTR_FROM must be dd-mm-yyyy" | Pass (25-Sep-2026) | GSTR_FROM=2026/09/01: stopped before the test started - "GSTR_FROM must be dd-mm-yyyy"

## MIS Report Check
MIS Report Check - run_mis_check.js
Opens every report under every MIS page, classifies the result, records report definition and available columns, compares with the previous run, saves outputs to "MIS Reports" and emails a summary.
Run: npm start (on a server: CI=1 BROWSER_CHANNEL=chromium node run_mis_check.js)
TC ID | Feature | Test Scenario | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Status | Remarks
MIS-01 | Login | Automatic login with dealervalidUser | Positive | High | credentials.json | Run the checker |  | "Logged in." and the MIS menu is read | Pass (25-Sep-2026)
MIS-02 | Login | Automatic login fails | Negative | High | Bad credentials | Run by hand / on CI |  | By hand: asks to log in manually and press Enter. CI/headless: exits with code 1 and a clear message (no waiting) | Pass (25-Sep-2026) | CI=1 with a wrong password and a fresh profile: exit 1 "Manual login needed but no one is at the terminal"
MIS-03 | Discovery | All MIS pages found | Positive | High | Logged in | Read the MIS menu |  | 11 pages; the duplicate "MIS" entry is skipped | Pass (25-Sep-2026) | 274 reports
MIS-04 | Filters | Default date range | Positive | Medium |  | Run with no fromDate/toDate |  | 1st of the month to yesterday (whole previous month on the 1st) | Pass (25-Sep-2026) | 01/09/2026 - 24/09/2026
MIS-05 | Classification | Report with data | Positive | High |  | View Report |  | OK | Pass (25-Sep-2026)
MIS-06 | Classification | Report over 1000 rows | Edge | High |  | View Report |  | OK - "Over display limit (downloads as Excel)" | Pass (25-Sep-2026) | Was wrongly "blank" before 25-Sep fix
MIS-07 | Classification | ASP.NET server error page | Negative | High |  | View Report |  | SERVER ERROR with the error text | Pass (25-Sep-2026) | e.g. TCS Transaction Details
MIS-08 | Classification | Crystal Reports viewer script missing on the server | Negative | High | crv.js returns 404 | View a Report.aspx report |  | SERVER ERROR "Crystal viewer script crv.js not served (HTTP 404) - page shows blank" | Pass (25-Sep-2026) | Root cause found 25-Sep; DMS server fix needed
MIS-09 | Classification | Report slower than 30s | Negative | Medium |  | View Report |  | TIMEOUT; one retry with a 1-day range (90s) only to read its columns | Pass (25-Sep-2026)
MIS-10 | Extra inputs | Report needs more than dates | Edge | High | extraInputs in CONFIG | View Report; DMS asks for input | Chassis P7BAAAXX1KS016088, Spare part R106020383, current month/year, 90 days, first Group-by | Values filled only when asked, report retried, form restored afterwards; "Needs extra input" dropped 15 -> 1 | Pass (25-Sep-2026) | Needs extra input 15 -> 1. Dead Stock now: Purchase Date today-3, Workshop 6, CounterSale 9 days (also the MFR "...Mfr" fields); spare part / chassis only when asked. Remaining: Mandatory part order details (list empty)
MIS-11 | New-tab reports | Report opens its own page | Edge | High |  | Select report (SetTab window.open) | e.g. Appointment Retention Metrics, VOR Details | Page opened in a real tab; headings of the visible data table used as objects | Pass (25-Sep-2026)
MIS-12 | Metadata | Report definition captured | Positive | Medium |  | Read the description under each report name |  | Report Definition column filled | Pass (25-Sep-2026)
MIS-13 | Metadata | Objects (columns) captured | Positive | High |  | Read Customize Columns list; else grid header |  | Objects Available filled | Pass (25-Sep-2026) | Not possible for failed / Crystal reports
MIS-14 | Output | Formatted Excel | Positive | High |  | Run completes |  | MIS Reports/MIS_Report_Objects_<stamp>.xlsx: grouped + merged by page/section; red = failed or missing name/definition; orange = no objects; "Changes vs Previous" sheet | Pass (25-Sep-2026)
MIS-15 | Output | CSV, summary and snapshot | Positive | Medium |  | Run completes |  | CSV, TXT summary and JSON snapshot in "MIS Reports" | Pass (25-Sep-2026)
MIS-16 | Comparison | Compare with the previous run | Positive | High | Earlier snapshot in "MIS Reports" | Run again |  | Added / removed / moved / columns-changed listed (only pages checked in both runs) | Pass (25-Sep-2026) | 14:40 run vs 14:21: 0 changes
MIS-17 | Comparison | No previous run | Edge | Low | Empty folder | Run |  | "This run is the baseline" message | Pass (25-Sep-2026)
MIS-18 | Email | Summary email with Excel attached | Positive | High | GMAIL_* in .env | Run completes |  | HTML summary (cards, changes, failures) emailed to GMAIL_TO with the Excel attached | Pass (25-Sep-2026) | Sent 15:14 to sunita@rideriver.com
MIS-19 | Email | Email not configured / fails | Negative | Low | GMAIL_* missing or SMTP down | Run completes |  | Email skipped or error logged (2 min limit); files still saved | Pass (25-Sep-2026) | Wrong Gmail password: "Email failed: Invalid login" logged; files saved; exit 0
MIS-20 | Robustness | Page or run takes too long | Negative | High |  | Run |  | Page given up after 25 min (TIMEOUT); whole run stopped after MIS_MAX_MINUTES (default 60) with exit code 2 | Pass (25-Sep-2026) | MIS_MAX_MINUTES=1: stopped after 61s with exit code 2
MIS-21 | Robustness | Browser missing / profile in use | Negative | Medium | Chrome not installed, or a second run started | Run |  | Exit code 1 with instructions (BROWSER_CHANNEL / wait for the other run) | Pass (25-Sep-2026) | chrome-canary: exit 1 "Could not start the browser..."; second run on the same profile: exit 1 with "wait for the other run"
MIS-22 | Options | Partial run without email | Positive | Low |  | CI=1 MIS_PAGES="CRM Reports" MIS_SEND_EMAIL=0 node run_mis_check.js |  | Only that page checked, headless, no email, exit code 0 | Pass (25-Sep-2026)
MIS-23 | Options | Credentials file and browser profile from settings | Positive | Medium | CREDENTIALS_FILE, MIS_PROFILE_DIR set | Run the checker |  | Logs in with that file using that profile folder | Pass (25-Sep-2026) | Used for MIS-02 / MIS-21 on 25-Sep

## PDI Vehicle Details
PDI Vehicle Details - tests/PDI.spec.ts
For every dealer in PIDUsers: find WORKSHOP > PDI rows with a blank field (all vehicles, not just the top 25), fill Engine / Battery / Charger from the VIN Details sheet in SETTINGS > Admin > Modify vehicle details, Save and confirm; per-dealer results in Output, plus a daily combined report.
Run: npm run test:pdi (dry run: npm run test:pdi:dry, daily report: npm run report:pdi-daily)
TC ID | Feature | Test Scenario | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Status | Remarks
PDI-01 | Setup | No PIDUsers, or a dealer with a missing / placeholder login | Negative | High | PIDUsers empty, or a dealer still on <user>/<password> | Start the run |  | Stops before any login, naming the dealer(s); nothing is changed | Pass (28-Sep-2026) | 292006 with <user>/<password>: stopped at once (message wording from an earlier build)
PDI-02 | Setup | Unknown dealer code in PDI_DEALER | Negative | Medium | PDI_RUN=1 | PDI_DEALER=999999 npx playwright test tests/PDI.spec.ts | PDI_DEALER=999999 | Stops at once: "PDI_DEALER: dealer 999999 is not in credentials.json." | Pass (28-Sep-2026) | Exact message seen; no login attempted
PDI-03 | Setup | Dealer listed twice in PIDUsers | Edge | Low | 332008 entered twice | Start the run |  | WARN "listed more than once — running it once"; dealer processed once | Pass (28-Sep-2026) | 332008 ran once
PDI-04 | Setup | VIN Details workbook missing | Negative | High | PDI_RUN=1 | PDI_VIN_FILE=C:\nope\missing.xlsx npx playwright test tests/PDI.spec.ts | PDI_VIN_FILE (missing file) | Stops at once: "VIN Details workbook not found ... (set PDI_VIN_FILE)" | Pass (28-Sep-2026) | Exact message seen; no login attempted
PDI-05 | Setup | PDI_TOP is not a number | Negative | Low | PDI_RUN=1 | PDI_TOP=abc npx playwright test tests/PDI.spec.ts | PDI_TOP=abc | Stops at once: "PDI_TOP must be a whole number above 0" | Pass (28-Sep-2026) | Exact message seen
PDI-06 | Safety | PDI specs are not run by a plain npm test / run-tests.bat | Negative | High | PDI_RUN not set | npx playwright test tests/PDI.spec.ts tests/PDIDailyReport.spec.ts |  | Both specs skipped — no DMS changes | Pass (28-Sep-2026) | "2 skipped"
PDI-07 | Login | Each PIDUsers dealer logs in | Positive | High | Real logins in PIDUsers | Dealer Code + Tab, User Name, Password, Sign In; log out / clear session before the next dealer | PIDUsers (15 dealers) | Dashboard verified for every dealer | Pass (28-Sep-2026) | 15/15 dealers across the 28-Sep runs
PDI-08 | Login | Wrong login for one dealer | Negative | High | One dealer with a bad login | Run with several dealers (dry run) | Scratch credentials: D71001 + fake dealer 999998 | That dealer marked failed (screenshot attached); other dealers still run; test red | Pass (28-Sep-2026) | 999998: "Login failed: still on the login page"; D71001 still processed; run red with both problems listed
PDI-09 | Navigation | Open WORKSHOP > PDI | Positive | High | Logged in | Click WORKSHOP, then PDI (matched by link, as menu names carry an icon) |  | PDI grid (PDIStockCheckingMain.aspx) is shown | Pass (28-Sep-2026) | Worked for all dealers
PDI-10 | PDI grid | List every vehicle, not just the top 25 | Positive | High | PDI page open | Set "Top" to PDI_TOP (500) and click Show before reading the grid | PDI_TOP=500 (default) | All vehicles listed; WARN if the list is full | Pass (28-Sep-2026) | D71001: 25 -> 28 vehicles, 10 -> 11 blank (one blank chassis had been hidden)
PDI-11 | PDI grid | Rows with a blank field are found | Positive | High | PDI grid loaded | Read inputs //input[starts-with(@id,"ctl00_cpMain_grdMain_")], group by row, keep rows with any empty field and save their ChassisNo |  | Chassis numbers listed with the blank field names | Pass (28-Sep-2026) | EngineNo was the blank field on every dealer
PDI-12 | PDI grid | PDI grid is empty | Edge | Medium | Dealer with no vehicles waiting for PDI | Open PDI | 271001 | "PDI grid is empty", "Nothing to update"; Modify page not opened | Pass (28-Sep-2026) | 271001
PDI-13 | PDI grid | No blank rows | Edge | Medium | Every PDI row filled | Open PDI |  | "0 PDI row(s) with blank fields", "Nothing to update" | Pass (28-Sep-2026) | e.g. 292005, 292010, and dealers re-checked after being updated
PDI-14 | Navigation | Open SETTINGS > Admin > Modify vehicle details | Positive | High | Blank rows found | SETTINGS > Admin > Modify vehicle details |  | ChangeChassisNo.aspx is shown | Pass (28-Sep-2026)
PDI-15 | Modify vehicle | Show loads the chassis | Positive | High | Modify page open | Enter chassis in ctl00$cpMain$IdentifierValue, click Show, wait 10 s | Chassis from the PDI grid | Form shows the same ChassisNo | Pass (28-Sep-2026)
PDI-16 | VIN lookup | Fill details from the VIN Details sheet | Positive | High | resources/VIN Details (1).xlsx | Find chassis in col A; col C -> EngineNo, col B -> BatteryDetails, col D -> VehicleChargerNo; EditChassisReason = "Details updated" | VIN Details (1).xlsx (29,814 VINs) | All four fields filled with the sheet's values | Pass (28-Sep-2026)
PDI-17 | VIN lookup | Chassis not in the VIN Details sheet | Negative | High |  | Run with a chassis missing from the sheet (dry run) | Copy of the VIN sheet without P7BAABXX1JT059691 | Skipped and listed as "Not in VIN Details sheet"; other chassis continue; test red | Pass (28-Sep-2026) | D71001: P7BAABXX1JT059691 skipped and listed; run red
PDI-18 | Save | Save and confirm the DMS kept the values | Positive | High | Form filled | Click Save (ctl00_cpMain_cmdSave), Show again, compare Engine / Battery / Charger |  | Status "Updated"; chassis number logged | Pass (28-Sep-2026) | 160 chassis updated across 12 dealers on 28-Sep
PDI-19 | Dry run | Fill the form without saving | Positive | High | PDI_DRY_RUN=1 | npm run test:pdi:dry |  | Form filled for every blank chassis, Save never clicked | Pass (28-Sep-2026) | D71001: 10 filled (morning run); 10 of 11 filled + 1 not in VIN sheet (negative test); nothing saved
PDI-20 | Output | Results Excel with a Dealers sheet | Positive | Medium |  | Run ends |  | Output/PDI_BlankChassis_<time>.xlsx: one row per chassis + every dealer checked | Pass (28-Sep-2026)
PDI-21 | Output | Results Excel is open in Excel (locked) | Edge | Medium | File locked | Run ends / daily report written |  | Saved beside it as <name>_<timestamp>.xlsx; run continues | Pass (28-Sep-2026) | Locked PDI_Daily_2026-09-28.xlsx: EBUSY -> saved as _1790610722383.xlsx, run passed
PDI-22 | Dashboard | Interactive dashboard | Positive | Medium | PDI_Dashboard.html (saved in Output) | Open in a browser; click a dealer bar, outcome chips, search, sort columns, theme toggle, phone width |  | Table filters / sorts correctly; dark mode and phone layout work | Pass (28-Sep-2026) | Sample data: dealer + Error filter -> "2 of 14"; no script errors; no sideways scroll at 390 px
PDI-23 | Daily report | Combine the day's runs | Positive | High | Result files in Output | npm run report:pdi-daily |  | Latest result per chassis; dry runs left out; errors cleared by a later check shown as Updated | Pass (28-Sep-2026) | 28-Sep: 5 runs -> 160 chassis, 15 dealers; 372002's 4 timeouts shown as Updated
PDI-24 | Daily report | No runs on that day | Negative | Low |  | PDI_REPORT_DATE=2020-01-01 npm run report:pdi-daily | PDI_REPORT_DATE=2020-01-01 | Stops: "No PDI result files from 2020-01-01" | Pass (28-Sep-2026) | Exact message seen
PDI-25 | Master | PDI master keeps the last 3 days | Positive | High | PDI_Daily files for 29-Sep, 30-Sep and 01-Oct in Output | npm run report:pdi-daily (any rebuild of the daily report) |  | Output/PDI_Master.xlsx: Tracking sheet, then one sheet per day for the last 3 days (newest first); older PDI files deleted, GSTR/other outputs untouched | Pass (01-Oct-2026) | Sheets: Tracking, 2026-10-01 (90 chassis), 2026-09-30 (237), 2026-09-29 (371)
PDI-26 | Daily report | Build a past day's report without emailing | Positive | Medium | Run files for that day in Output/PDI runs | PDI_RUN=1 PDI_REPORT_DATE=2026-09-30 PDI_SEND_EMAIL=0 npx playwright test tests/PDIDailyReport.spec.ts | PDI_REPORT_DATE=2026-09-30, PDI_SEND_EMAIL=0 | PDI_Daily_<day>.xlsx built from that day's runs and added to the master; no email sent | Pass (01-Oct-2026) | 30-Sep: 3 runs -> 237 chassis, 85 dealers; "PDI_SEND_EMAIL=0 — report email skipped"
PDI-27 | Tracking | All-time totals and day-wise running totals | Positive | High | Output/PDI_History.json (filled by every daily rebuild) | Rebuild the daily report; open the Tracking sheet of PDI_Master.xlsx | 29-Sep to 01-Oct history | KPIs: total chassis found, total updated, no usable VIN data (still open), errors (still open); one row per day with that day's counts and running totals | Pass (01-Oct-2026) | 693 found / 679 updated / 14 no VIN / 0 errors; running totals found 371 -> 607 -> 693, updated 370 -> 603 -> 679
PDI-28 | Dashboard | PDI master dashboard | Positive | Medium | Output/PDI_Master.html (saved in Output, not emailed) | Open in a browser: KPI tiles, day-wise bars (click a day to filter), dealer x day table, chassis table with filters/search/sort; theme toggle; phone width |  | All sections render and filter; dark mode and phone layout work | Pass (01-Oct-2026) | No script errors; no sideways scroll at 390 px; light and dark checked
PDI-29 | Email | "Till now" KPIs and day-wise tracking in the email body | Positive | High | PDI history present | PDI_RUN=1 PDI_EMAIL_REVIEW=1 PDI_FORCE_EMAIL=1 npx playwright test tests/PDIDailyReport.spec.ts |  | Email body shows total chassis found / updated / no usable VIN data (still open) since the first day, and a day-wise table (last 14 days) with running totals | Pending review | Review copy sent 01-Oct-2026 with 693 / 679 / 14; layout to be confirmed by the report owner
PDI-30 | Email | Only Excel files are attached | Positive | Medium | PDI_Master.xlsx in Output | Send the daily report |  | Attachments: PDI_Daily_<day>.xlsx and PDI_Master.xlsx; no HTML files | Pending review | Review copy sent 01-Oct-2026; to be confirmed in the inbox
PDI-31 | Email | Review copy goes to the report owner only | Positive | High | Today's email already sent | PDI_RUN=1 PDI_EMAIL_REVIEW=1 PDI_FORCE_EMAIL=1 npx playwright test tests/PDIDailyReport.spec.ts | PDI_EMAIL_REVIEW=1 | Sent to GMAIL_TO only, subject starts [REVIEW], no CC; the day's "emailed" marker is not changed | Pass (01-Oct-2026) | "Report emailed to sunita@rideriver.com." (no cc); emailed_2026-10-01.txt still "sent 11:48"
PDI-32 | Email | Daily email is not sent twice | Negative | High | Today's email already sent | Run npm run report:pdi-daily again the same day |  | Report files rebuilt; email skipped with a message | Pass (01-Oct-2026) | "Today's PDI email already went out (sent 1/10/2026, 11:48:52 am) — not sending it again"
PDI-33 | VIN lookup | Newest VIN*.xlsx in resources/ is used, whatever its exact name | Edge | Medium | resources/ has "VIN Details.xlsx" and a newer "VIN.xlsx"; PDI_VIN_FILE not set | Start the run; check the "VIN sheet:" line in the dashboard / Excel subtitle | VIN.xlsx (headers: VIN, Battery No, Motor No, Charger No) | VIN.xlsx is used (newest match); any VIN….xlsx name works; Excel lock files (~$…) are ignored; PDI_VIN_FILE still overrides | Pending live run | 06-Oct-2026: file choice checked without the DMS (newer VIN.xlsx picked over VIN Details.xlsx; VIN Details.xlsx picked again once VIN.xlsx was removed)

## Stage DMS Flow
Stage DMS Flow - tests/Automation for Testing.spec.ts
One River User login on the stage DMS, then the full pre-sales to receipt flow on a new customer each run: enquiry, follow-up, booking from the enquiry and a receipt against the booking. Creates real records on stage only.
Run: npx playwright test "tests/Automation for Testing.spec.ts"
TC ID | Feature | Test Scenario | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Status | Remarks
STG-01 | Login | River User logs in to the stage DMS | Positive | High | stageUser in credentials.json | 1. Open https://stage.rivermobility.gaindms.com/ 2. Click River User 3. Enter User Name, Password 4. Click Sign In | stageUser | User dashboard opens (userdashboard.aspx) on the stage host; user menu and PRESALES menu visible; login form gone; session cookie set; no alerts | Pass (06-Oct-2026) | Spec test TC01. The other scenarios reuse this one login (no login / logout per scenario). The suite refuses to run if STAGE_URL is not a stage. host.
STG-02 | Enquiry | Create a new enquiry with the mandatory fields | Positive | High | Logged in (STG-01) | 1. My Enquiries: search the run's mobile - 0 records 2. New 3. Primary / Secondary DataSource: Walk-in 4. Title, Name, Mobile, State, City, Pin Code 5. Model, Product, Color (autosuggest, first match) 6. Enquiry Category, Step to Sale, Follow-up date (tomorrow) / time, Summary, Loan Required 7. Check every field kept its value, then Save | Name "Auto Test <runId>", mobile 9<runId>0, Karnataka / Bengaluru / 560001, Model Gen, Hot – 30 days, Enquiry assigned, 10:00, Loan No | Save postback is sent (no client-side alert); My Enquiries by mobile shows exactly 1 record with the name, mobile, today's date, tomorrow's follow-up and status Hot | Pass (06-Oct-2026) | Spec test TC02. 06-Oct run: Auto Test 74325818 / 9743258180, Gen-3, INDIE GEN-3 MONSOON BLUE - 750W CHARGER, Monsoon Blue
STG-03 | Follow-up | Add a follow-up to the new enquiry | Positive | High | Enquiry from STG-02 | 1. My Enquiries: search by mobile, open the enquiry 2. Check the saved enquiry details 3. Follow Up tab: check pre-filled date, time, Followup by, category, status (disabled, Hot) 4. Call Mode, Primary / Secondary reason, Call note, Step to Sale, Next call date (+2 days) / time 5. Update Followup | Telephone, Needs More Time / Customer asked to follow up later, Test Ride Scheduled, next call today+2 11:00 | "Followup updated" shown, no alerts, form cleared, same enquiry; one Activity Log entry with today, the next call date and Step to Sale; My Enquiries row shows the new follow-up date instead of tomorrow's | Pass (06-Oct-2026) | Spec test TC03. 06-Oct run: next call 08/10/2026 11:00
STG-04 | Booking | Create a booking from the enquiry | Positive | High | Enquiry from STG-02 | 1. My Enquiries: search by mobile, tick the row 2. Booking (opens a new tab) 3. Check the 8 fields pre-filled from the enquiry 4. Finance Type, RTO Type, Insurance Type 5. Save Booking | Full cash, Permanent, Insurance By Dealer | Booking Info form pre-filled (date, sales exec, customer, mobile, place of supply, state, city, pin, product, colour, data source locked); after Save the Receipt page opens with booking no. (dealer/yy/IND/n), total > 0 and balance = total; no alerts; the enquiry leaves My Enquiries (0 records) | Pass (06-Oct-2026) | Spec test TC04. 06-Oct run: booking 372007/26/IND/13, total ₹161,499.45
STG-05 | Receipt | Make a receipt against the booking | Positive | High | Booking from STG-04 | 1. Sales > Vehicle sales: filter by mobile, open the booking 2. Customer Center: check booking no., customer, totals (paid 0) 3. Make Receipt 4. Check the pre-filled receipt (reference, names, mode, branch / franchise / company, account, Cash) 5. Amount, Narration, SAVE | ₹5,000, narration "Booking advance by Playwright automation (stage) <runId>" | "Last receipt saved was <receipt no>"; no alerts; form cleared; receipt row with today, ₹5,000.00, Complete Product Sale Value, Cancel / Print; Customer Center shows Total Paid 5,000.00 and Balance = total - 5,000 | Pass (06-Oct-2026) | Spec test TC05. 06-Oct run: receipt 37200726Ca00019, balance ₹156,499.45

## Coverage Gaps
Item | Gap | Suggested action
Removed on 25-Sep (moved to "E2E DMS_removed_2026-09-25") | Finance Dashboard helpers (utils/appsScriptSheet.ts, utils/excelExport.ts, resources/apps-script), unused Spares page objects, old tests/MIS Report_Check.js, requirements.txt, specs/, resources/credentials.ts | Nothing - kept outside the project only as a backup
playwright.config.ts "setup" project | Matches *.setup.ts but no such file exists; "Google Chrome" project expects playwright/.auth/salesforce.json (both specs override it with an empty session) | Fixed (28-Sep-2026): setup and enroll-passkey projects and the unused saved-login file removed from playwright.config.ts; Enquiry List passed with the new config
tests/enquiryListReport.spec.ts | From date hard-coded to 7 Sep 2026 | Fixed (28-Sep-2026): ENQ_FROM / ENQ_TO (dd-mm-yyyy), default unchanged (07-09-2026 to today) — see ENQ-16 / ENQ-17
CI/CD (.github/workflows/playwright.yml) | Not yet run on GitHub Actions; needs repository secrets CREDENTIALS_JSON, GMAIL_USER, GMAIL_APP_PASSWORD, GMAIL_TO | Needs the repository owner: add the secrets under Settings > Secrets and variables > Actions, then run the workflow once (cannot be done from this PC — no GitHub CLI / secret values are private)
tests/PDI.spec.ts — PDI grid size | Only the rows the PDI page shows are checked (Top N = 25 by default); blank rows further down are missed | Fixed (28-Sep-2026): the spec sets "Top" to PDI_TOP (500) and clicks Show; warns if the list is full — see the "top 25" PDI case
tests/PDI.spec.ts — fixed 10 s wait after Show | Asked for by the process; slow DMS responses beyond 10 s are caught by the ChassisNo check (PDI-14) but not waited for | Keep; switch to waiting for the ChassisNo field if it proves flaky
tests/Automation for Testing.spec.ts – records left on stage | Every run adds a new enquiry, booking and ₹5,000 receipt on stage (unique name / mobile per run); nothing is cancelled afterwards | Fine for stage; add a clean-up step (cancel receipt / booking) if the stage data needs to stay tidy
tests/Automation for Testing.spec.ts – TC06 | Placeholder (test.fixme) with no scenario yet | Define scenario 6, then add it to the Stage DMS Flow sheet